## Inspections
Inspection ID | Case ID | Inspection Date | Inspection Type | Inspector Company | Inspection Result | Defects Found | Rectification Required | Rectification Deadline | Rectification Completed | Follow up Inspection Date | Inspection Cost Sgd
INS-2018-001 | UP-2023-217 | 03 Mar 2028 | SAFETY | Quality Assurance International | PASS | 0 | FALSE |  | FALSE | 28 Aug 2028 | 6125
INS-2018-002 | UP-2019-047 | 29 Nov 2027 | QUALITY_CONTROL | Quality Assurance International | FAIL | 10 | TRUE | 22 Jan 2028 | TRUE | 03 Dec 2028 | 19195
INS-2018-003 | UP-2021-145 | 05 Oct 2028 | QUALITY_CONTROL | Urbania Partners | FAIL | 23 | TRUE | 06 Aug 2028 | TRUE | 18 Aug 2028 | 18471
INS-2018-004 | UP-2019-056 | 04 May 2024 | QUALITY_CONTROL | Environmental Compliance Unit | PASS_WITH_ADVISORY | 17 | FALSE |  | FALSE | 09 Dec 2024 | 4023
INS-2018-005 | UP-2018-001 | 08 Apr 2019 | ENVIRONMENTAL | BuildCheck Services | PASS | 8 | TRUE | 08 Dec 2019 | FALSE | 11 Aug 2019 | 10891
INS-2018-006 | UP-2023-226 | 27 Jan 2021 | FINAL_INSPECTION | Quality Assurance International | FAIL | 40 | TRUE | 23 Feb 2021 | TRUE | 14 Feb 2021 | 13987
INS-2018-007 | UP-2024-279 | 24 Oct 2020 | QUALITY_CONTROL | BuildCheck Services | FAIL | 38 | TRUE | 13 Dec 2020 | FALSE | 28 Feb 2021 | 21933
INS-2018-008 | UP-2024-274 | 11 Nov 2021 | STRUCTURAL | BuildCheck Services | FAIL | 36 | TRUE | 17 Dec 2021 | FALSE | 23 Feb 2022 | 3753
INS-2018-009 | UP-2020-090 | 13 Jul 2028 | PROGRESS_REVIEW | BuildCheck Services | FAIL | 31 | FALSE |  | FALSE | 29 Nov 2028 | 18338
INS-2018-010 | UP-2019-075 | 17 Jun 2026 | FINAL_INSPECTION | Urbania Partners | PASS | 14 | FALSE |  | FALSE | 09 Nov 2026 | 6715
INS-2018-011 | UP-2022-162 | 28 Dec 2022 | QUALITY_CONTROL | BuildCheck Services | FAIL | 34 | FALSE |  | FALSE | 03 Dec 2023 | 20399
INS-2018-012 | UP-2022-163 | 25 Sep 2024 | PROGRESS_REVIEW | BuildCheck Services | FAIL | 40 | TRUE | 28 Oct 2024 | FALSE | 20 Oct 2024 | 1433
INS-2018-013 | UP-2024-260 | 18 Sep 2027 | FINAL_INSPECTION | Environmental Compliance Unit | FAIL | 33 | TRUE | 11 Jun 2027 | TRUE | 23 Nov 2027 | 4747
INS-2018-014 | UP-2021-148 | 02 Apr 2025 | QUALITY_CONTROL | TechVerify Consulting | FAIL | 24 | TRUE | 04 May 2025 | TRUE | 03 Nov 2025 | 1380
INS-2018-015 | UP-2021-156 | 27 Aug 2027 | ENVIRONMENTAL | Quality Assurance International | FAIL | 36 | TRUE | 19 Oct 2027 | TRUE | 20 Jan 2028 | 20032
INS-2018-016 | UP-2024-279 | 23 Nov 2022 | ENVIRONMENTAL | Building Standards Division | FAIL | 25 | FALSE |  | FALSE | 02 Aug 2023 | 1134
INS-2018-017 | UP-2019-072 | 05 Jun 2023 | PROGRESS_REVIEW | Environmental Compliance Unit | PASS_WITH_ADVISORY | 18 | FALSE |  | FALSE | 15 Sep 2023 | 11300
INS-2018-018 | UP-2019-056 | 17 Nov 2025 | PROGRESS_REVIEW | BuildCheck Services | PASS | 13 | FALSE |  | FALSE | 13 Mar 2026 | 3872
INS-2018-019 | UP-2019-054 | 07 Dec 2024 | SITE_AUDIT | Quality Assurance International | FAIL | 22 | TRUE | 26 Aug 2024 | TRUE | 10 Aug 2024 | 16131
INS-2018-020 | UP-2024-244 | 23 May 2021 | STRUCTURAL | Environmental Compliance Unit | FAIL | 11 | TRUE | 07 May 2021 | TRUE | 09 Jun 2021 | 16184
INS-2018-021 | UP-2021-139 | 27 Sep 2024 | SITE_AUDIT | TechVerify Consulting | FAIL | 27 | TRUE | 20 Oct 2024 | TRUE | 03 Aug 2025 | 13071
INS-2018-022 | UP-2024-277 | 30 Oct 2027 | SITE_AUDIT | BuildCheck Services | FAIL | 22 | TRUE | 20 Nov 2027 | FALSE | 13 Apr 2028 | 13595
INS-2018-023 | UP-2020-094 | 01 Jul 2022 | ENVIRONMENTAL | Environmental Compliance Unit | FAIL | 27 | FALSE |  | FALSE | 30 Jan 2022 | 19688
INS-2018-024 | UP-2018-002 | 14 Apr 2026 | STRUCTURAL | BuildCheck Services | PASS | 14 | FALSE |  | FALSE | 13 May 2026 | 16226
INS-2018-025 | UP-2018-023 | 10 Sep 2027 | SUSTAINABILITY_VERIFICATION | Quality Assurance International | PASS_WITH_ADVISORY | 17 | FALSE |  | FALSE | 31 Dec 2027 | 19818
INS-2018-026 | UP-2020-103 | 03 Jul 2025 | PROGRESS_REVIEW | Urbania Partners | FAIL | 22 | TRUE | 31 Mar 2025 | FALSE | 16 May 2025 | 1914
INS-2018-027 | UP-2023-203 | 01 Dec 2029 | SITE_AUDIT | Building Standards Division | PASS_WITH_ADVISORY | 19 | FALSE |  | FALSE | 16 Apr 2029 | 6074
INS-2018-028 | UP-2019-068 | 18 Nov 2026 | QUALITY_CONTROL | Environmental Compliance Unit | FAIL | 23 | TRUE | 29 Nov 2026 | TRUE | 27 Jan 2027 | 15360
INS-2018-029 | UP-2021-158 | 16 Jul 2027 | SAFETY | TechVerify Consulting | FAIL | 32 | TRUE | 08 Feb 2027 | FALSE | 29 Aug 2027 | 11839
INS-2018-030 | UP-2024-262 | 10 May 2024 | PROGRESS_REVIEW | BuildCheck Services | FAIL | 24 | FALSE |  | FALSE | 01 Oct 2025 | 3874
INS-2018-031 | UP-2022-186 | 09 Jun 2019 | STRUCTURAL | Urbania Partners | FAIL | 13 | TRUE | 17 Sep 2019 | FALSE | 15 Nov 2019 | 21683
INS-2018-032 | UP-2019-048 | 08 Jul 2024 | QUALITY_CONTROL | TechVerify Consulting | FAIL | 34 | TRUE | 09 Mar 2024 | FALSE | 18 Nov 2024 | 24765
INS-2018-033 | UP-2022-178 | 07 Nov 2026 | SAFETY | TechVerify Consulting | PASS | 13 | FALSE |  | FALSE | 21 Dec 2026 | 3951
INS-2018-034 | UP-2023-234 | 19 Mar 2025 | SITE_AUDIT | Environmental Compliance Unit | PASS | 15 | FALSE |  | FALSE | 30 May 2025 | 4969
INS-2018-035 | UP-2021-160 | 26 Jul 2023 | SITE_AUDIT | Urbania Partners | FAIL | 22 | TRUE | 09 Jul 2023 | TRUE | 11 Aug 2023 | 8459
INS-2018-036 | UP-2018-016 | 04 Jan 2022 | ENVIRONMENTAL | Building Standards Division | FAIL | 27 | TRUE | 04 Aug 2022 | FALSE | 26 Jun 2022 | 8269
INS-2018-037 | UP-2023-233 | 25 Jun 2026 | ENVIRONMENTAL | TechVerify Consulting | PASS | 9 | FALSE |  | FALSE | 20 Nov 2026 | 5088
INS-2018-038 | UP-2024-255 | 03 Jun 2020 | PROGRESS_REVIEW | Quality Assurance International | FAIL | 31 | TRUE | 04 Aug 2020 | FALSE | 05 Nov 2020 | 19720
INS-2018-039 | UP-2019-045 | 07 Mar 2020 | ENVIRONMENTAL | Urbania Partners | FAIL | 21 | TRUE | 08 Sep 2020 | FALSE | 29 Nov 2020 | 19319
INS-2018-040 | UP-2020-108 | 29 Mar 2024 | QUALITY_CONTROL | Building Standards Division | PASS | 12 | FALSE |  | FALSE | 24 Jul 2024 | 1545
INS-2019-041 | UP-2020-081 | 20 Nov 2027 | SUSTAINABILITY_VERIFICATION | TechVerify Consulting | FAIL | 37 | TRUE | 17 Jan 2028 | TRUE | 22 Dec 2027 | 22987
INS-2019-042 | UP-2018-035 | 26 Oct 2023 | STRUCTURAL | TechVerify Consulting | PASS | 11 | FALSE |  | FALSE | 21 Dec 2023 | 5472
INS-2019-043 | UP-2018-004 | 17 Oct 2021 | STRUCTURAL | TechVerify Consulting | FAIL | 34 | TRUE | 11 Sep 2021 | FALSE | 17 Dec 2021 | 19819
INS-2019-044 | UP-2021-128 | 29 May 2026 | ENVIRONMENTAL | TechVerify Consulting | PASS | 10 | FALSE |  | FALSE | 25 Jul 2026 | 10699
INS-2019-045 | UP-2019-052 | 03 Jan 2028 | FINAL_INSPECTION | Environmental Compliance Unit | FAIL | 35 | TRUE | 04 Dec 2028 | FALSE | 26 May 2028 | 22879
INS-2019-046 | UP-2019-069 | 12 Feb 2028 | SAFETY | Environmental Compliance Unit | FAIL | 28 | TRUE | 22 Jan 2029 | FALSE | 17 Jan 2029 | 16661
INS-2019-047 | UP-2022-189 | 02 Nov 2024 | SUSTAINABILITY_VERIFICATION | Urbania Partners | PASS_WITH_ADVISORY | 17 | FALSE |  | FALSE | 14 Mar 2024 | 24740
INS-2019-048 | UP-2020-091 | 27 Feb 2024 | SAFETY | Building Standards Division | FAIL | 21 | TRUE | 04 May 2024 | FALSE | 07 Aug 2024 | 7134
INS-2019-049 | UP-2020-100 | 30 Apr 2023 | PROGRESS_REVIEW | Environmental Compliance Unit | PASS | 1 | FALSE |  | FALSE | 20 Aug 2023 | 1687
INS-2019-050 | UP-2022-161 | 17 May 2027 | QUALITY_CONTROL | Quality Assurance International | FAIL | 20 | TRUE | 29 May 2027 | TRUE | 31 Oct 2027 | 19455
INS-2019-051 | UP-2020-093 | 06 Jul 2027 | SAFETY | Environmental Compliance Unit | PASS | 19 | FALSE |  | FALSE | 07 Apr 2027 | 14433
INS-2019-052 | UP-2021-146 | 02 Jun 2021 | PROGRESS_REVIEW | Quality Assurance International | PASS | 40 | TRUE | 03 Mar 2021 | TRUE | 23 Apr 2021 | 21803
INS-2019-053 | UP-2021-147 | 20 Jan 2022 | FINAL_INSPECTION | TechVerify Consulting | PASS_WITH_ADVISORY | 18 | FALSE |  | FALSE | 17 Apr 2022 | 21665
INS-2019-054 | UP-2022-168 | 24 Feb 2021 | SITE_AUDIT | Quality Assurance International | FAIL | 22 | TRUE | 31 Mar 2021 | FALSE | 14 Jul 2021 | 19833
INS-2019-055 | UP-2021-124 | 05 Dec 2025 | SUSTAINABILITY_VERIFICATION | BuildCheck Services | FAIL | 33 | TRUE | 06 May 2025 | TRUE | 08 Jan 2025 | 16578
INS-2019-056 | UP-2019-063 | 14 May 2024 | SITE_AUDIT | Building Standards Division | PASS | 4 | FALSE |  | FALSE | 06 Mar 2024 | 6710
INS-2019-057 | UP-2020-111 | 13 Feb 2022 | SAFETY | TechVerify Consulting | FAIL | 16 | TRUE | 03 Feb 2022 | FALSE | 05 May 2022 | 18832
INS-2019-058 | UP-2022-167 | 29 Jun 2026 | SITE_AUDIT | Building Standards Division | FAIL | 16 | TRUE | 13 Aug 2026 | FALSE | 29 Sep 2026 | 22006
INS-2019-059 | UP-2023-212 | 24 Sep 2024 | SUSTAINABILITY_VERIFICATION | BuildCheck Services | FAIL | 30 | TRUE | 20 Oct 2024 | TRUE | 11 Nov 2024 | 8281
INS-2019-060 | UP-2019-070 | 06 Feb 2023 | SUSTAINABILITY_VERIFICATION | Urbania Partners | PASS_WITH_ADVISORY | 17 | FALSE |  | FALSE | 29 Sep 2023 | 9061
INS-2019-061 | UP-2020-086 | 12 Aug 2023 | SUSTAINABILITY_VERIFICATION | TechVerify Consulting | PASS | 11 | FALSE |  | FALSE | 16 Feb 2024 | 9814
INS-2019-062 | UP-2020-100 | 25 Nov 2025 | SAFETY | Environmental Compliance Unit | FAIL | 22 | TRUE | 01 Aug 2026 | TRUE | 16 Mar 2026 | 10825
INS-2019-063 | UP-2018-040 | 10 Apr 2023 | SITE_AUDIT | Urbania Partners | FAIL | 23 | TRUE | 12 Feb 2023 | TRUE | 12 Jul 2023 | 24722
INS-2019-064 | UP-2021-131 | 28 Dec 2025 | ENVIRONMENTAL | Quality Assurance International | FAIL | 27 | TRUE | 01 Apr 2026 | FALSE | 23 Jun 2026 | 22181
INS-2019-065 | UP-2020-084 | 10 Mar 2025 | QUALITY_CONTROL | Environmental Compliance Unit | PASS_WITH_ADVISORY | 19 | FALSE |  | FALSE | 15 Nov 2025 | 8086
INS-2019-066 | UP-2020-086 | 16 Mar 2021 | FINAL_INSPECTION | Quality Assurance International | PASS | 15 | FALSE |  | FALSE | 09 Nov 2021 | 17407
INS-2019-067 | UP-2020-084 | 18 Jan 2026 | PROGRESS_REVIEW | Quality Assurance International | FAIL | 36 | TRUE | 27 Feb 2026 | TRUE | 14 Jun 2026 | 6945
INS-2019-068 | UP-2020-118 | 12 Jun 2024 | SAFETY | Quality Assurance International | PASS | 11 | FALSE |  | FALSE | 03 Jun 2025 | 8661
INS-2019-069 | UP-2019-059 | 01 Sep 2019 | QUALITY_CONTROL | BuildCheck Services | FAIL | 39 | TRUE | 02 Jun 2019 | FALSE | 03 Jun 2019 | 12028
INS-2019-070 | UP-2018-030 | 14 May 2022 | QUALITY_CONTROL | Environmental Compliance Unit | PASS | 4 | FALSE |  | FALSE | 22 Jun 2022 | 13315
INS-2019-071 | UP-2021-135 | 16 Aug 2021 | STRUCTURAL | Environmental Compliance Unit | FAIL | 26 | TRUE | 17 Sep 2021 | TRUE | 02 Aug 2022 | 9027
INS-2019-072 | UP-2021-147 | 11 Sep 2024 | PROGRESS_REVIEW | Building Standards Division | PASS | 7 | FALSE |  | FALSE | 04 Oct 2025 | 20143
INS-2019-073 | UP-2019-051 | 09 Feb 2023 | ENVIRONMENTAL | Quality Assurance International | PASS_WITH_ADVISORY | 17 | FALSE |  | FALSE | 23 Dec 2023 | 1278
INS-2019-074 | UP-2023-224 | 21 Nov 2029 | FINAL_INSPECTION | TechVerify Consulting | PASS | 12 | FALSE |  | FALSE | 20 Dec 2029 | 21919
INS-2019-075 | UP-2022-181 | 07 Mar 2025 | SUSTAINABILITY_VERIFICATION | Quality Assurance International | PASS | 5 | FALSE |  | FALSE | 21 Sep 2025 | 23110
INS-2019-076 | UP-2024-267 | 12 Aug 2022 | STRUCTURAL | Building Standards Division | FAIL | 21 | TRUE | 17 Dec 2022 | TRUE | 02 Jul 2023 | 10987
INS-2019-077 | UP-2024-280 | 06 Jun 2024 | SAFETY | BuildCheck Services | PASS | 11 | FALSE |  | FALSE | 16 Oct 2024 | 22833
INS-2019-078 | UP-2022-199 | 21 Jul 2023 | FINAL_INSPECTION | Urbania Partners | PASS | 15 | FALSE |  | FALSE | 13 Sep 2023 | 23343
INS-2019-079 | UP-2022-170 | 17 Sep 2019 | QUALITY_CONTROL | Quality Assurance International | PASS | 9 | FALSE |  | FALSE | 12 Sep 2019 | 2373
INS-2019-080 | UP-2024-243 | 18 May 2026 | FINAL_INSPECTION | Urbania Partners | PASS | 13 | FALSE |  | FALSE | 17 Jul 2026 | 18709
INS-2020-081 | UP-2020-084 | 06 Jul 2025 | PROGRESS_REVIEW | Environmental Compliance Unit | PASS_WITH_ADVISORY | 18 | FALSE |  | FALSE | 07 Jan 2025 | 8897
INS-2020-082 | UP-2021-155 | 03 Jul 2023 | SAFETY | BuildCheck Services | FAIL | 23 | TRUE | 16 Mar 2023 | TRUE | 04 Jan 2023 | 12001
INS-2020-083 | UP-2023-240 | 30 Nov 2024 | SUSTAINABILITY_VERIFICATION | TechVerify Consulting | FAIL | 32 | TRUE | 13 Dec 2024 | FALSE | 24 Dec 2024 | 7210
INS-2020-084 | UP-2024-279 | 04 Jul 2021 | SUSTAINABILITY_VERIFICATION | Building Standards Division | FAIL | 27 | TRUE | 23 Apr 2021 | TRUE | 23 Jun 2021 | 13207
INS-2020-085 | UP-2023-237 | 18 Dec 2023 | ENVIRONMENTAL | Quality Assurance International | PASS | 5 | FALSE |  | FALSE | 22 May 2024 | 9243
INS-2020-086 | UP-2023-240 | 02 Nov 2025 | SAFETY | Environmental Compliance Unit | FAIL | 24 | TRUE | 29 Mar 2025 | TRUE | 15 May 2025 | 18488
INS-2020-087 | UP-2023-209 | 10 Sep 2026 | FINAL_INSPECTION | Quality Assurance International | FAIL | 27 | TRUE | 26 Oct 2026 | FALSE | 02 Dec 2027 | 19645
INS-2020-088 | UP-2024-267 | 14 Jan 2023 | QUALITY_CONTROL | Urbania Partners | PASS | 6 | FALSE |  | FALSE | 27 Feb 2023 | 14357
INS-2020-089 | UP-2021-139 | 17 Mar 2027 | SITE_AUDIT | Building Standards Division | PASS | 6 | FALSE |  | FALSE | 14 Aug 2027 | 19310
INS-2020-090 | UP-2024-279 | 23 May 2021 | SITE_AUDIT | TechVerify Consulting | PASS_WITH_ADVISORY | 17 | FALSE |  | FALSE | 25 Jun 2021 | 22137
INS-2020-091 | UP-2023-216 | 07 Nov 2024 | SITE_AUDIT | Building Standards Division | FAIL | 34 | TRUE | 29 Jul 2024 | FALSE | 17 Oct 2024 | 11533
INS-2020-092 | UP-2018-032 | 02 Mar 2022 | SUSTAINABILITY_VERIFICATION | Urbania Partners | FAIL | 36 | TRUE | 03 Apr 2022 | FALSE | 17 Jun 2022 | 10996
INS-2020-093 | UP-2020-104 | 21 Sep 2023 | SAFETY | Environmental Compliance Unit | PASS | 1 | FALSE |  | FALSE | 22 Feb 2024 | 3913
INS-2020-094 | UP-2020-086 | 28 Oct 2022 | QUALITY_CONTROL | TechVerify Consulting | PASS | 16 | FALSE |  | FALSE | 29 Dec 2022 | 15939
INS-2020-095 | UP-2024-275 | 06 Jan 2026 | FINAL_INSPECTION | Quality Assurance International | PASS | 7 | FALSE |  | FALSE | 23 Sep 2026 | 18742
INS-2020-096 | UP-2019-051 | 22 Sep 2024 | FINAL_INSPECTION | Urbania Partners | FAIL | 38 | TRUE | 10 Jul 2024 | TRUE | 22 Oct 2024 | 9856
INS-2020-097 | UP-2021-123 | 06 Oct 2020 | PROGRESS_REVIEW | BuildCheck Services | PASS | 12 | FALSE |  | FALSE | 23 Oct 2020 | 22091
INS-2020-098 | UP-2018-013 | 03 May 2021 | SAFETY | Quality Assurance International | PASS | 16 | FALSE |  | FALSE | 04 Sep 2021 | 7600
INS-2020-099 | UP-2022-164 | 13 Oct 2027 | QUALITY_CONTROL | Building Standards Division | PASS | 3 | FALSE |  | FALSE | 26 Jan 2028 | 23373
INS-2020-100 | UP-2019-057 | 22 Sep 2027 | PROGRESS_REVIEW | TechVerify Consulting | FAIL | 20 | TRUE | 19 Oct 2027 | FALSE | 02 Dec 2028 | 9555
INS-2020-101 | UP-2020-114 | 14 Feb 2025 | ENVIRONMENTAL | TechVerify Consulting | PASS | 14 | FALSE |  | FALSE | 06 Aug 2025 | 24129
INS-2020-102 | UP-2022-169 | 01 Mar 2028 | SITE_AUDIT | TechVerify Consulting | FAIL | 29 | TRUE | 22 Jan 2028 | TRUE | 21 Mar 2028 | 16845
INS-2020-103 | UP-2022-192 | 22 Jan 2023 | FINAL_INSPECTION | Building Standards Division | PASS | 11 | FALSE |  | FALSE | 21 Apr 2023 | 6559
INS-2020-104 | UP-2019-076 | 08 Sep 2023 | ENVIRONMENTAL | BuildCheck Services | FAIL | 23 | TRUE | 24 Aug 2023 | TRUE | 09 Jul 2023 | 20709
INS-2020-105 | UP-2024-268 | 05 Nov 2027 | SAFETY | Urbania Partners | FAIL | 28 | TRUE | 06 Nov 2027 | TRUE | 08 Sep 2027 | 23729
INS-2020-106 | UP-2018-038 | 19 Feb 2025 | QUALITY_CONTROL | Environmental Compliance Unit | PASS | 8 | FALSE |  | FALSE | 06 May 2025 | 14985
INS-2020-107 | UP-2023-207 | 08 Aug 2027 | ENVIRONMENTAL | BuildCheck Services | PASS | 4 | FALSE |  | FALSE | 16 Sep 2027 | 12751
INS-2020-108 | UP-2023-210 | 02 Oct 2023 | SITE_AUDIT | BuildCheck Services | FAIL | 33 | TRUE | 30 Mar 2023 | TRUE | 03 Sep 2023 | 12696
INS-2020-109 | UP-2023-211 | 17 Mar 2028 | ENVIRONMENTAL | TechVerify Consulting | FAIL | 26 | TRUE | 25 Mar 2028 | FALSE | 14 May 2028 | 5531
INS-2020-110 | UP-2019-072 | 13 Nov 2021 | FINAL_INSPECTION | Building Standards Division | PASS | 15 | FALSE |  | FALSE | 05 Sep 2022 | 16310
INS-2020-111 | UP-2020-102 | 07 Feb 2023 | SUSTAINABILITY_VERIFICATION | Quality Assurance International | FAIL | 22 | TRUE | 27 Jul 2023 | FALSE | 19 Jul 2023 | 14425
INS-2020-112 | UP-2021-160 | 31 May 2026 | STRUCTURAL | Environmental Compliance Unit | PASS | 16 | FALSE |  | FALSE | 07 Oct 2026 | 15570
INS-2020-113 | UP-2019-043 | 08 Sep 2026 | QUALITY_CONTROL | Building Standards Division | FAIL | 36 | TRUE | 10 Apr 2026 | FALSE | 10 Jul 2026 | 16455
INS-2020-114 | UP-2020-098 | 14 Jun 2022 | SITE_AUDIT | BuildCheck Services | PASS | 5 | FALSE |  | FALSE | 23 Oct 2022 | 14803
INS-2020-115 | UP-2018-007 | 28 Apr 2021 | SAFETY | BuildCheck Services | FAIL | 29 | TRUE | 06 Sep 2021 | TRUE | 19 Jul 2021 | 5339
INS-2020-116 | UP-2020-113 | 12 Apr 2026 | FINAL_INSPECTION | Environmental Compliance Unit | FAIL | 33 | TRUE | 13 Dec 2026 | FALSE | 30 May 2027 | 14092
INS-2020-117 | UP-2023-215 | 21 Aug 2026 | SITE_AUDIT | BuildCheck Services | PASS | 13 | FALSE |  | FALSE | 28 Oct 2026 | 9809
INS-2020-118 | UP-2019-054 | 21 Mar 2019 | STRUCTURAL | TechVerify Consulting | PASS | 7 | FALSE |  | FALSE | 08 Feb 2019 | 22267
INS-2020-119 | UP-2018-030 | 12 Apr 2022 | PROGRESS_REVIEW | BuildCheck Services | FAIL | 21 | TRUE | 01 Apr 2023 | FALSE | 22 Dec 2022 | 15415
INS-2020-120 | UP-2022-180 | 15 Sep 2028 | QUALITY_CONTROL | TechVerify Consulting | PASS | 12 | FALSE |  | FALSE | 02 Jul 2029 | 11129
INS-2021-121 | UP-2018-027 | 22 Aug 2022 | SAFETY | Building Standards Division | FAIL | 23 | TRUE | 28 Sep 2022 | TRUE | 27 Oct 2022 | 20434
INS-2021-122 | UP-2022-165 | 07 Apr 2026 | SITE_AUDIT | BuildCheck Services | FAIL | 22 | TRUE | 28 Aug 2026 | TRUE | 09 Mar 2026 | 6494
INS-2021-123 | UP-2022-185 | 04 Mar 2024 | PROGRESS_REVIEW | Environmental Compliance Unit | PASS | 13 | FALSE |  | FALSE | 13 May 2024 | 19840
INS-2021-124 | UP-2020-104 | 05 Nov 2024 | SAFETY | BuildCheck Services | PASS | 9 | FALSE |  | FALSE | 10 Oct 2024 | 2138
INS-2021-125 | UP-2022-169 | 23 May 2027 | STRUCTURAL | TechVerify Consulting | FAIL | 38 | TRUE | 18 Jun 2027 | FALSE | 20 Oct 2027 | 21717
INS-2021-126 | UP-2018-037 | 15 May 2022 | SAFETY | Environmental Compliance Unit | FAIL | 21 | TRUE | 25 Jun 2022 | FALSE | 25 Jul 2022 | 14644
INS-2021-127 | UP-2024-242 | 02 Nov 2026 | PROGRESS_REVIEW | Building Standards Division | FAIL | 20 | TRUE | 25 Feb 2026 | FALSE | 04 Feb 2026 | 6491
INS-2021-128 | UP-2022-176 | 25 Jul 2020 | SITE_AUDIT | Building Standards Division | FAIL | 33 | TRUE | 17 Aug 2020 | FALSE | 16 Nov 2020 | 11289
INS-2021-129 | UP-2024-264 | 24 Dec 2022 | PROGRESS_REVIEW | BuildCheck Services | FAIL | 34 | TRUE | 29 Jan 2023 | TRUE | 25 May 2023 | 14805
INS-2021-130 | UP-2023-225 | 04 Jul 2025 | SAFETY | Building Standards Division | FAIL | 40 | TRUE | 22 May 2025 | FALSE | 24 Apr 2025 | 14229
INS-2021-131 | UP-2018-031 | 21 Jan 2025 | STRUCTURAL | Environmental Compliance Unit | FAIL | 23 | TRUE | 02 Mar 2025 | FALSE | 13 Apr 2025 | 14144
INS-2021-132 | UP-2021-153 | 20 Jun 2022 | SUSTAINABILITY_VERIFICATION | TechVerify Consulting | FAIL | 22 | TRUE | 07 Jun 2022 | FALSE | 15 Oct 2022 | 19412
INS-2021-133 | UP-2023-220 | 25 Aug 2023 | STRUCTURAL | Quality Assurance International | FAIL | 24 | TRUE | 21 Sep 2023 | FALSE | 02 Apr 2024 | 3336
INS-2021-134 | UP-2023-219 | 23 Dec 2023 | PROGRESS_REVIEW | TechVerify Consulting | PASS | 16 | FALSE |  | FALSE | 16 Feb 2024 | 24396
INS-2021-135 | UP-2021-142 | 05 Aug 2023 | FINAL_INSPECTION | Building Standards Division | PASS | 7 | FALSE |  | FALSE | 29 Oct 2023 | 18328
INS-2021-136 | UP-2023-227 | 01 Dec 2028 | ENVIRONMENTAL | TechVerify Consulting | FAIL | 24 | TRUE | 30 Jan 2028 | TRUE | 19 Jun 2028 | 4489
INS-2021-137 | UP-2019-075 | 08 Aug 2022 | ENVIRONMENTAL | TechVerify Consulting | PASS | 7 | FALSE |  | FALSE | 15 Sep 2022 | 11436
INS-2021-138 | UP-2024-278 | 04 Jan 2026 | SITE_AUDIT | Building Standards Division | FAIL | 22 | TRUE | 05 Aug 2026 | FALSE | 15 May 2026 | 3181
INS-2021-139 | UP-2018-015 | 18 Dec 2023 | SAFETY | BuildCheck Services | FAIL | 23 | TRUE | 02 Jul 2024 | TRUE | 23 Feb 2024 | 21414
INS-2021-140 | UP-2019-044 | 22 Nov 2025 | FINAL_INSPECTION | Building Standards Division | FAIL | 28 | TRUE | 24 Dec 2025 | FALSE | 02 Jul 2026 | 16263
INS-2021-141 | UP-2020-107 | 11 Dec 2024 | QUALITY_CONTROL | Quality Assurance International | FAIL | 32 | TRUE | 19 Dec 2024 | TRUE | 27 Apr 2025 | 12469
INS-2021-142 | UP-2018-015 | 14 Nov 2019 | PROGRESS_REVIEW | Urbania Partners | PASS | 0 | FALSE |  | FALSE | 12 Sep 2019 | 5322
INS-2021-143 | UP-2023-237 | 17 Jul 2026 | ENVIRONMENTAL | TechVerify Consulting | FAIL | 33 | TRUE | 28 Jul 2026 | FALSE | 08 Nov 2026 | 17773
INS-2021-144 | UP-2019-072 | 22 Aug 2022 | PROGRESS_REVIEW | Quality Assurance International | PASS_WITH_ADVISORY | 19 | FALSE |  | FALSE | 14 Dec 2022 | 23382
INS-2021-145 | UP-2021-129 | 22 Aug 2024 | PROGRESS_REVIEW | Environmental Compliance Unit | FAIL | 21 | TRUE | 21 Oct 2024 | TRUE | 26 Dec 2024 | 24757
INS-2021-146 | UP-2023-235 | 14 Mar 2026 | SUSTAINABILITY_VERIFICATION | Urbania Partners | FAIL | 37 | TRUE | 04 Aug 2026 | TRUE | 07 Feb 2026 | 14592
INS-2021-147 | UP-2020-115 | 26 Dec 2021 | ENVIRONMENTAL | TechVerify Consulting | PASS_WITH_ADVISORY | 18 | FALSE |  | FALSE | 30 Apr 2022 | 23734
INS-2021-148 | UP-2020-083 | 21 Nov 2023 | FINAL_INSPECTION | Environmental Compliance Unit | FAIL | 21 | TRUE | 12 Aug 2023 | TRUE | 18 Mar 2024 | 4240
INS-2021-149 | UP-2024-277 | 03 Dec 2023 | QUALITY_CONTROL | BuildCheck Services | FAIL | 36 | TRUE | 21 Mar 2023 | FALSE | 19 Apr 2023 | 17133
INS-2021-150 | UP-2020-095 | 26 Dec 2026 | SAFETY | Environmental Compliance Unit | PASS | 8 | FALSE |  | FALSE | 15 Mar 2027 | 3894
INS-2021-151 | UP-2021-127 | 07 May 2025 | PROGRESS_REVIEW | Urbania Partners | FAIL | 26 | TRUE | 21 Jul 2025 | TRUE | 10 Jan 2025 | 18863
INS-2021-152 | UP-2020-112 | 04 Mar 2024 | ENVIRONMENTAL | Quality Assurance International | PASS | 14 | FALSE |  | FALSE | 29 Aug 2024 | 10069
INS-2021-153 | UP-2023-226 | 07 Mar 2021 | ENVIRONMENTAL | BuildCheck Services | PASS | 6 | FALSE |  | FALSE | 26 Nov 2021 | 11331
INS-2021-154 | UP-2019-058 | 23 Jul 2027 | QUALITY_CONTROL | TechVerify Consulting | FAIL | 24 | TRUE | 18 Aug 2027 | FALSE | 19 Aug 2027 | 9423
INS-2021-155 | UP-2019-070 | 25 Jul 2022 | STRUCTURAL | TechVerify Consulting | FAIL | 40 | TRUE | 08 Dec 2022 | FALSE | 12 Dec 2022 | 1113
INS-2021-156 | UP-2020-093 | 25 May 2028 | ENVIRONMENTAL | BuildCheck Services | PASS | 9 | FALSE |  | FALSE | 20 Oct 2028 | 7287
INS-2021-157 | UP-2021-141 | 11 Apr 2027 | QUALITY_CONTROL | Urbania Partners | FAIL | 30 | TRUE | 24 Dec 2027 | TRUE | 18 Apr 2028 | 10868
INS-2021-158 | UP-2023-234 | 11 May 2025 | SUSTAINABILITY_VERIFICATION | Quality Assurance International | PASS | 13 | FALSE |  | FALSE | 27 Jan 2026 | 20364
INS-2021-159 | UP-2020-094 | 22 Jun 2025 | SITE_AUDIT | Building Standards Division | PASS | 12 | FALSE |  | FALSE | 27 Sep 2025 | 20509
INS-2021-160 | UP-2019-048 | 29 Jun 2027 | SITE_AUDIT | Quality Assurance International | FAIL | 3 | TRUE | 29 Jul 2027 | FALSE | 10 Sep 2027 | 15717
INS-2022-161 | UP-2018-021 | 10 Dec 2028 | STRUCTURAL | Quality Assurance International | PASS | 10 | FALSE |  | FALSE | 19 Nov 2028 | 4779
INS-2022-162 | UP-2024-261 | 03 Jan 2023 | ENVIRONMENTAL | Quality Assurance International | FAIL | 21 | TRUE | 24 Apr 2023 | FALSE | 27 Jun 2023 | 7650
INS-2022-163 | UP-2024-261 | 09 Jul 2021 | ENVIRONMENTAL | Environmental Compliance Unit | FAIL | 39 | TRUE | 23 Sep 2021 | TRUE | 31 Oct 2021 | 6765
INS-2022-164 | UP-2020-086 | 20 Aug 2024 | SAFETY | BuildCheck Services | FAIL | 25 | TRUE | 21 Sep 2024 | FALSE | 30 Jan 2025 | 17709
INS-2022-165 | UP-2019-043 | 27 Feb 2025 | SUSTAINABILITY_VERIFICATION | Urbania Partners | FAIL | 30 | TRUE | 25 Apr 2025 | FALSE | 07 Jul 2025 | 1072
INS-2022-166 | UP-2018-024 | 22 Mar 2027 | ENVIRONMENTAL | TechVerify Consulting | PASS | 2 | FALSE |  | FALSE | 26 Aug 2027 | 12386
INS-2022-167 | UP-2021-149 | 23 May 2026 | QUALITY_CONTROL | Building Standards Division | PASS | 6 | FALSE |  | FALSE | 09 Feb 2026 | 18991
INS-2022-168 | UP-2020-087 | 14 May 2027 | QUALITY_CONTROL | Building Standards Division | PASS | 16 | FALSE |  | FALSE | 14 Oct 2027 | 18887
INS-2022-169 | UP-2019-049 | 30 Sep 2022 | SAFETY | Quality Assurance International | FAIL | 21 | TRUE | 23 Oct 2022 | FALSE | 26 Oct 2022 | 7355
INS-2022-170 | UP-2018-016 | 26 Aug 2024 | ENVIRONMENTAL | BuildCheck Services | FAIL | 23 | TRUE | 15 Oct 2024 | TRUE | 12 Aug 2024 | 7476
INS-2022-171 | UP-2021-138 | 02 Nov 2022 | SAFETY | TechVerify Consulting | PASS | 10 | FALSE |  | FALSE | 04 Mar 2022 | 4555
INS-2022-172 | UP-2020-090 | 10 Sep 2027 | SITE_AUDIT | TechVerify Consulting | FAIL | 29 | TRUE | 11 Nov 2027 | TRUE | 11 Dec 2027 | 19449
INS-2022-173 | UP-2020-104 | 18 Jan 2029 | SAFETY | TechVerify Consulting | FAIL | 40 | TRUE | 03 Oct 2029 | TRUE | 14 Feb 2029 | 19743
INS-2022-174 | UP-2022-164 | 11 Sep 2024 | QUALITY_CONTROL | Quality Assurance International | PASS_WITH_ADVISORY | 18 | FALSE |  | FALSE | 14 Apr 2025 | 23161
INS-2022-175 | UP-2018-029 | 03 Jun 2022 | STRUCTURAL | Environmental Compliance Unit | PASS | 11 | FALSE |  | FALSE | 24 Aug 2022 | 18920
INS-2022-176 | UP-2023-227 | 08 Aug 2027 | FINAL_INSPECTION | Building Standards Division | PASS | 6 | FALSE |  | FALSE | 24 Nov 2027 | 17098
INS-2022-177 | UP-2022-168 | 05 Feb 2024 | SAFETY | Urbania Partners | FAIL | 27 | TRUE | 18 Jun 2024 | FALSE | 06 Jul 2024 | 22256
INS-2022-178 | UP-2019-061 | 12 Sep 2025 | SAFETY | Quality Assurance International | PASS | 15 | FALSE |  | FALSE | 19 Jan 2026 | 3578
INS-2022-179 | UP-2021-144 | 21 Dec 2023 | QUALITY_CONTROL | Quality Assurance International | PASS | 10 | FALSE |  | FALSE | 05 Jun 2024 | 4465
INS-2022-180 | UP-2020-093 | 21 Apr 2025 | STRUCTURAL | Quality Assurance International | FAIL | 22 | TRUE | 29 Apr 2025 | FALSE | 06 Dec 2025 | 22303
INS-2022-181 | UP-2018-025 | 17 May 2027 | SUSTAINABILITY_VERIFICATION | Quality Assurance International | PASS | 11 | FALSE |  | FALSE | 07 Nov 2027 | 22820
INS-2022-182 | UP-2018-001 | 08 May 2022 | ENVIRONMENTAL | Building Standards Division | PASS | 4 | FALSE |  | FALSE | 01 Feb 2023 | 9022
INS-2022-183 | UP-2022-182 | 17 Nov 2024 | SUSTAINABILITY_VERIFICATION | Quality Assurance International | PASS | 7 | FALSE |  | FALSE | 02 May 2025 | 3516
INS-2022-184 | UP-2023-211 | 20 Aug 2026 | ENVIRONMENTAL | BuildCheck Services | PASS | 8 | FALSE |  | FALSE | 25 Jan 2027 | 20982
INS-2022-185 | UP-2023-213 | 04 Mar 2026 | STRUCTURAL | Quality Assurance International | FAIL | 22 | TRUE | 04 Nov 2026 | TRUE | 24 Sep 2026 | 15860
INS-2022-186 | UP-2023-202 | 12 Dec 2026 | PROGRESS_REVIEW | Environmental Compliance Unit | PASS | 8 | FALSE |  | FALSE | 19 Apr 2027 | 12620
INS-2022-187 | UP-2019-058 | 10 Jul 2027 | SAFETY | Quality Assurance International | PASS | 4 | FALSE |  | FALSE | 22 Feb 2028 | 5923
INS-2022-188 | UP-2019-044 | 16 Jul 2026 | QUALITY_CONTROL | Urbania Partners | PASS | 11 | FALSE |  | FALSE | 18 Dec 2026 | 8053
INS-2022-189 | UP-2020-115 | 14 Nov 2023 | SAFETY | Building Standards Division | PASS_WITH_ADVISORY | 19 | FALSE |  | FALSE | 04 Apr 2024 | 17512
INS-2022-190 | UP-2021-148 | 09 Oct 2023 | SUSTAINABILITY_VERIFICATION | Urbania Partners | PASS | 13 | TRUE | 16 Oct 2023 | FALSE | 12 Jan 2023 | 12710
INS-2022-191 | UP-2018-004 | 20 Oct 2024 | STRUCTURAL | Quality Assurance International | FAIL | 38 | FALSE |  | FALSE | 12 Jan 2024 | 1560
INS-2022-192 | UP-2024-272 | 02 Jul 2028 | SAFETY | TechVerify Consulting | FAIL | 22 | TRUE | 29 Feb 2028 | FALSE | 07 Apr 2028 | 19914
INS-2022-193 | UP-2023-240 | 17 Jun 2025 | PROGRESS_REVIEW | BuildCheck Services | PASS | 16 | FALSE |  | FALSE | 07 Dec 2025 | 1012
INS-2022-194 | UP-2020-081 | 23 Jan 2024 | ENVIRONMENTAL | Urbania Partners | PASS | 15 | FALSE |  | FALSE | 28 May 2024 | 8514
INS-2022-195 | UP-2018-006 | 15 Apr 2026 | SUSTAINABILITY_VERIFICATION | Building Standards Division | FAIL | 22 | TRUE | 13 Jun 2026 | TRUE | 14 Jul 2026 | 13718
INS-2022-196 | UP-2021-141 | 09 Oct 2027 | STRUCTURAL | Building Standards Division | PASS | 12 | FALSE |  | FALSE | 25 Sep 2027 | 15562
INS-2022-197 | UP-2019-058 | 03 Dec 2023 | FINAL_INSPECTION | Building Standards Division | FAIL | 21 | TRUE | 19 Mar 2023 | FALSE | 04 Aug 2023 | 2143
INS-2022-198 | UP-2021-131 | 26 May 2021 | ENVIRONMENTAL | Quality Assurance International | PASS | 12 | FALSE |  | FALSE | 28 Jun 2021 | 15148
INS-2022-199 | UP-2023-214 | 19 Nov 2025 | ENVIRONMENTAL | TechVerify Consulting | PASS | 4 | FALSE |  | FALSE | 25 Feb 2026 | 8247
INS-2022-200 | UP-2021-126 | 12 Jan 2021 | QUALITY_CONTROL | Environmental Compliance Unit | PASS | 3 | FALSE |  | FALSE | 02 Nov 2022 | 2449
INS-2023-201 | UP-2020-103 | 29 Aug 2023 | SUSTAINABILITY_VERIFICATION | Environmental Compliance Unit | PASS | 8 | FALSE |  | FALSE | 27 Dec 2023 | 9201
INS-2023-202 | UP-2021-129 | 19 Oct 2028 | PROGRESS_REVIEW | BuildCheck Services | FAIL | 33 | TRUE | 11 Jul 2028 | FALSE | 02 Feb 2029 | 9394
INS-2023-203 | UP-2021-155 | 14 Oct 2021 | ENVIRONMENTAL | Urbania Partners | PASS | 11 | FALSE |  | FALSE | 04 Oct 2022 | 18586
INS-2023-204 | UP-2023-230 | 21 Sep 2023 | SUSTAINABILITY_VERIFICATION | BuildCheck Services | PASS | 4 | FALSE |  | FALSE | 03 May 2024 | 8637
INS-2023-205 | UP-2019-078 | 03 Jul 2026 | SITE_AUDIT | Environmental Compliance Unit | FAIL | 30 | TRUE | 04 Apr 2026 | FALSE | 07 Nov 2026 | 23333
INS-2023-206 | UP-2019-054 | 02 Sep 2023 | ENVIRONMENTAL | Urbania Partners | FAIL | 39 | TRUE | 26 Feb 2023 | FALSE | 17 May 2023 | 11498
INS-2023-207 | UP-2020-096 | 30 Jan 2026 | STRUCTURAL | Urbania Partners | PASS | 11 | FALSE |  | FALSE | 13 Apr 2026 | 20093
INS-2023-208 | UP-2019-069 | 06 Apr 2028 | SITE_AUDIT | BuildCheck Services | FAIL | 34 | TRUE | 07 May 2028 | FALSE | 20 Jul 2028 | 13329
INS-2023-209 | UP-2018-004 | 02 Jun 2025 | FINAL_INSPECTION | Quality Assurance International | PASS | 0 | FALSE |  | FALSE | 05 Oct 2025 | 19546
INS-2023-210 | UP-2024-277 | 04 Nov 2024 | ENVIRONMENTAL | Environmental Compliance Unit | PASS | 5 | FALSE |  | FALSE | 22 Jul 2024 | 14934
INS-2023-211 | UP-2018-030 | 28 Feb 2022 | ENVIRONMENTAL | BuildCheck Services | PASS_WITH_ADVISORY | 19 | FALSE |  | FALSE | 13 Jul 2022 | 3633
INS-2023-212 | UP-2024-257 | 17 May 2028 | SUSTAINABILITY_VERIFICATION | Environmental Compliance Unit | PASS | 9 | FALSE |  | FALSE | 28 Jun 2028 | 6008
INS-2023-213 | UP-2020-084 | 07 Jun 2022 | SITE_AUDIT | BuildCheck Services | FAIL | 32 | TRUE | 24 Aug 2022 | FALSE | 26 Oct 2022 | 23414
INS-2023-214 | UP-2022-192 | 19 Jun 2021 | SITE_AUDIT | TechVerify Consulting | FAIL | 34 | TRUE | 14 Jul 2021 | TRUE | 18 Sep 2021 | 15453
INS-2023-215 | UP-2023-225 | 05 Mar 2029 | QUALITY_CONTROL | Urbania Partners | FAIL | 41 | TRUE | 15 May 2029 | TRUE | 16 Oct 2029 | 6857
INS-2023-216 | UP-2023-206 | 03 Aug 2029 | STRUCTURAL | Environmental Compliance Unit | FAIL | 32 | TRUE | 23 Apr 2029 | FALSE | 20 Jul 2029 | 9101
INS-2023-217 | UP-2018-025 | 11 Oct 2028 | ENVIRONMENTAL | Building Standards Division | FAIL | 22 | TRUE | 01 Feb 2029 | FALSE | 28 Feb 2029 | 15241
INS-2023-218 | UP-2021-125 | 17 Apr 2026 | SITE_AUDIT | Building Standards Division | PASS | 5 | FALSE |  | FALSE | 14 Oct 2026 | 5545
INS-2023-219 | UP-2020-116 | 01 Jun 2024 | PROGRESS_REVIEW | Building Standards Division | FAIL | 24 | TRUE | 29 Feb 2024 | TRUE | 15 Jun 2024 | 8825
INS-2023-220 | UP-2020-095 | 07 Nov 2022 | SUSTAINABILITY_VERIFICATION | TechVerify Consulting | PASS | 3 | FALSE |  | FALSE | 22 Nov 2022 | 13020
INS-2023-221 | UP-2022-198 | 24 Jun 2022 | QUALITY_CONTROL | Quality Assurance International | PASS_WITH_ADVISORY | 19 | FALSE |  | FALSE | 12 Aug 2022 | 3755
INS-2023-222 | UP-2018-021 | 28 Oct 2025 | ENVIRONMENTAL | TechVerify Consulting | FAIL | 28 | TRUE | 12 Mar 2025 | TRUE | 01 Oct 2026 | 13865
INS-2023-223 | UP-2020-096 | 15 Apr 2023 | SITE_AUDIT | Urbania Partners | FAIL | 23 | TRUE | 06 Jul 2023 | TRUE | 21 Sep 2023 | 12883
INS-2023-224 | UP-2020-097 | 23 Dec 2021 | FINAL_INSPECTION | BuildCheck Services | PASS | 13 | FALSE |  | FALSE | 31 May 2022 | 20364
INS-2023-225 | UP-2024-242 | 22 May 2022 | QUALITY_CONTROL | Quality Assurance International | PASS | 14 | FALSE |  | FALSE | 07 Aug 2022 | 8700
INS-2023-226 | UP-2024-243 | 14 Dec 2021 | SAFETY | Building Standards Division | FAIL | 21 | TRUE | 19 Jan 2022 | FALSE | 20 May 2022 | 8613
INS-2023-227 | UP-2021-122 | 07 Jun 2021 | STRUCTURAL | Building Standards Division | PASS | 12 | FALSE |  | FALSE | 11 Nov 2021 | 14977
INS-2023-228 | UP-2022-181 | 18 Aug 2022 | ENVIRONMENTAL | Environmental Compliance Unit | FAIL | 36 | TRUE | 09 Oct 2022 | TRUE | 09 Oct 2022 | 3142
INS-2023-229 | UP-2019-042 | 08 Jan 2029 | SITE_AUDIT | Environmental Compliance Unit | PASS | 14 | FALSE |  | FALSE | 21 Dec 2029 | 23148
INS-2023-230 | UP-2021-128 | 23 Sep 2027 | STRUCTURAL | Urbania Partners | PASS | 11 | FALSE |  | FALSE | 01 May 2028 | 3916
INS-2023-231 | UP-2022-162 | 16 Apr 2021 | SUSTAINABILITY_VERIFICATION | Environmental Compliance Unit | FAIL | 34 | TRUE | 05 Mar 2021 | FALSE | 13 Jul 2021 | 7974
INS-2023-232 | UP-2022-191 | 04 Oct 2026 | ENVIRONMENTAL | Building Standards Division | PASS | 1 | FALSE |  | FALSE | 25 Jun 2026 | 19721
INS-2023-233 | UP-2021-134 | 06 Oct 2022 | SUSTAINABILITY_VERIFICATION | BuildCheck Services | PASS | 10 | FALSE |  | FALSE | 18 Aug 2022 | 4157
INS-2023-234 | UP-2019-045 | 17 Jun 2022 | STRUCTURAL | BuildCheck Services | PASS | 9 | FALSE |  | FALSE | 22 Nov 2022 | 20645
INS-2023-235 | UP-2018-006 | 15 May 2026 | QUALITY_CONTROL | TechVerify Consulting | PASS | 2 | FALSE |  | FALSE | 06 Sep 2026 | 21316
INS-2023-236 | UP-2023-219 | 16 Aug 2024 | QUALITY_CONTROL | TechVerify Consulting | FAIL | 40 | TRUE | 15 Oct 2024 | TRUE | 20 Nov 2024 | 11179
INS-2023-237 | UP-2021-157 | 03 Nov 2027 | ENVIRONMENTAL | BuildCheck Services | PASS | 12 | FALSE |  | FALSE | 07 Jun 2027 | 7445
INS-2023-238 | UP-2019-077 | 08 Jul 2028 | PROGRESS_REVIEW | Urbania Partners | FAIL | 21 | TRUE | 17 Sep 2028 | TRUE | 11 Oct 2028 | 7780
INS-2023-239 | UP-2021-123 | 11 Feb 2020 | SAFETY | Environmental Compliance Unit | FAIL | 23 | TRUE | 30 Nov 2020 | FALSE | 04 Oct 2021 | 16340
INS-2023-240 | UP-2021-135 | 10 Dec 2021 | STRUCTURAL | Environmental Compliance Unit | FAIL | 37 | TRUE | 11 Jan 2021 | FALSE | 30 Mar 2022 | 23496
INS-2024-241 | UP-2021-144 | 04 Feb 2025 | SUSTAINABILITY_VERIFICATION | TechVerify Consulting | FAIL | 27 | TRUE | 21 Apr 2025 | FALSE | 07 Sep 2025 | 1642
INS-2024-242 | UP-2022-178 | 12 Feb 2028 | STRUCTURAL | Building Standards Division | FAIL | 29 | TRUE | 26 Dec 2028 | TRUE | 21 Feb 2029 | 13743
INS-2024-243 | UP-2018-035 | 30 Mar 2025 | ENVIRONMENTAL | Quality Assurance International | PASS | 14 | FALSE |  | FALSE | 06 Dec 2025 | 19048
INS-2024-244 | UP-2023-211 | 10 Jun 2023 | STRUCTURAL | BuildCheck Services | FAIL | 32 | TRUE | 20 Nov 2023 | TRUE | 31 Jan 2024 | 1528
INS-2024-245 | UP-2019-074 | 17 May 2024 | STRUCTURAL | TechVerify Consulting | FAIL | 23 | TRUE | 28 Jun 2024 | FALSE | 19 Jun 2024 | 20851
INS-2024-246 | UP-2022-174 | 30 Jul 2027 | SAFETY | Building Standards Division | FAIL | 35 | TRUE | 21 Sep 2027 | TRUE | 17 Jan 2028 | 13974
INS-2024-247 | UP-2023-233 | 04 Dec 2023 | PROGRESS_REVIEW | TechVerify Consulting | PASS | 8 | FALSE |  | FALSE | 09 Jul 2023 | 9442
INS-2024-248 | UP-2020-114 | 21 Mar 2027 | QUALITY_CONTROL | TechVerify Consulting | FAIL | 30 | TRUE | 14 Apr 2027 | FALSE | 17 Jun 2027 | 9290
INS-2024-249 | UP-2019-045 | 22 Apr 2025 | ENVIRONMENTAL | TechVerify Consulting | FAIL | 22 | TRUE | 31 May 2025 | TRUE | 10 Jun 2025 | 20217
INS-2024-250 | UP-2023-227 | 27 Jul 2028 | SAFETY | Quality Assurance International | PASS | 13 | FALSE |  | FALSE | 11 Apr 2028 | 19719
INS-2024-251 | UP-2018-026 | 23 May 2026 | PROGRESS_REVIEW | TechVerify Consulting | PASS | 4 | FALSE |  | FALSE | 07 Mar 2026 | 13161
INS-2024-252 | UP-2023-240 | 04 Apr 2028 | SAFETY | Building Standards Division | PASS | 3 | FALSE |  | FALSE | 09 May 2028 | 15248
INS-2024-253 | UP-2020-082 | 02 Mar 2026 | SAFETY | Quality Assurance International | PASS | 0 | FALSE |  | FALSE | 21 Jul 2026 | 9545
INS-2024-254 | UP-2019-062 | 24 Feb 2024 | PROGRESS_REVIEW | TechVerify Consulting | PASS | 1 | FALSE |  | FALSE | 14 May 2024 | 17278
INS-2024-255 | UP-2019-070 | 24 Apr 2027 | STRUCTURAL | BuildCheck Services | FAIL | 31 | TRUE | 06 Apr 2027 | TRUE | 08 Nov 2027 | 20229
INS-2024-256 | UP-2020-100 | 09 Apr 2023 | SITE_AUDIT | Urbania Partners | FAIL | 26 | TRUE | 10 Dec 2023 | FALSE | 21 Sep 2023 | 24819
INS-2024-257 | UP-2018-022 | 13 Jul 2027 | FINAL_INSPECTION | Environmental Compliance Unit | PASS | 2 | FALSE |  | FALSE | 01 Apr 2028 | 18569
INS-2024-258 | UP-2018-009 | 22 Jul 2025 | ENVIRONMENTAL | Environmental Compliance Unit | PASS | 16 | FALSE |  | FALSE | 24 Sep 2025 | 9980
INS-2024-259 | UP-2023-203 | 27 Jun 2023 | QUALITY_CONTROL | Building Standards Division | PASS | 15 | FALSE |  | FALSE | 14 Dec 2023 | 6620
INS-2024-260 | UP-2023-208 | 24 Feb 2029 | SUSTAINABILITY_VERIFICATION | BuildCheck Services | FAIL | 34 | TRUE | 20 Apr 2029 | TRUE | 07 Sep 2029 | 22036
INS-2024-261 | UP-2019-058 | 11 Sep 2026 | SITE_AUDIT | Urbania Partners | FAIL | 40 | TRUE | 12 Aug 2026 | TRUE | 03 Dec 2027 | 1045
INS-2024-262 | UP-2018-027 | 10 Oct 2022 | STRUCTURAL | BuildCheck Services | PASS | 1 | FALSE |  | FALSE | 01 May 2023 | 3607
INS-2024-263 | UP-2018-019 | 11 Jun 2020 | PROGRESS_REVIEW | Urbania Partners | FAIL | 36 | TRUE | 12 Jan 2020 | FALSE | 27 Nov 2020 | 20168
INS-2024-264 | UP-2023-218 | 17 Nov 2024 | SUSTAINABILITY_VERIFICATION | Building Standards Division | PASS | 2 | FALSE |  | FALSE | 15 Jan 2025 | 21768
INS-2024-265 | UP-2020-098 | 20 Mar 2021 | ENVIRONMENTAL | TechVerify Consulting | FAIL | 40 | TRUE | 29 Mar 2021 | FALSE | 05 Aug 2021 | 8149
INS-2024-266 | UP-2021-122 | 06 Oct 2024 | QUALITY_CONTROL | TechVerify Consulting | FAIL | 33 | TRUE | 08 May 2024 | FALSE | 12 Jan 2024 | 10964
INS-2024-267 | UP-2024-256 | 23 Aug 2026 | STRUCTURAL | Environmental Compliance Unit | FAIL | 24 | TRUE | 17 Sep 2026 | FALSE | 09 Aug 2026 | 19339
INS-2024-268 | UP-2023-228 | 14 Mar 2028 | ENVIRONMENTAL | Quality Assurance International | PASS | 16 | FALSE |  | FALSE | 07 May 2028 | 2932
INS-2024-269 | UP-2024-260 | 31 Aug 2026 | QUALITY_CONTROL | Environmental Compliance Unit | FAIL | 30 | TRUE | 09 Sep 2026 | TRUE | 21 Jan 2027 | 23352
INS-2024-270 | UP-2023-217 | 13 Apr 2022 | STRUCTURAL | Urbania Partners | FAIL | 34 | TRUE | 06 Mar 2022 | TRUE | 15 Aug 2022 | 10673
INS-2025-310 | UP-2025-088 | 05 Aug 2025 | Pre-Construction Safety | Pulau Safety Consultants Pte Ltd | Pass | 0 | FALSE |  |  |  | 1200
INS-2023-014 | UP-2022-061 | 18 Jan 2023 | Safety | Ulu SafeCheck Pte Ltd | Fail | 5 | TRUE | 02 Jan 2023 | TRUE | 02 Oct 2023 | 850
INS-2023-029 | UP-2022-061 | 04 Dec 2023 | Structural | Ulu SafeCheck Pte Ltd | Pass | 1 | FALSE |  |  |  | 900
INS-2023-078 | UP-2023-018 | 22 Aug 2023 | Safety | Island Inspection Services | Fail | 7 | TRUE | 09 Dec 2023 | TRUE | 20 Sep 2023 | 850
INS-2023-112 | UP-2023-018 | 30 Nov 2023 | Structural | Island Inspection Services | Fail | 4 | TRUE | 21 Dec 2023 | TRUE | 01 May 2024 | 900
INS-2024-021 | UP-2023-095 | 14 Feb 2024 | Safety | Ulu SafeCheck Pte Ltd | Fail | 8 | TRUE | 03 Jul 2024 | TRUE | 15 Mar 2024 | 850
INS-2024-055 | UP-2023-095 | 06 Oct 2024 | Structural | Ulu SafeCheck Pte Ltd | Fail | 6 | TRUE | 07 Jan 2024 | TRUE | 07 Dec 2024 | 900
INS-2024-089 | UP-2023-095 | 10 Mar 2024 | Safety | Island Inspection Services | Pass | 2 | FALSE |  |  |  | 850
INS-2024-102 | UP-2024-032 | 19 Jul 2024 | Safety | Island Inspection Services | Fail | 5 | TRUE | 08 Sep 2024 | TRUE | 16 Aug 2024 | 850
INS-2024-138 | UP-2024-032 | 28 Nov 2024 | Structural | Ulu SafeCheck Pte Ltd | Fail | 3 | TRUE | 19 Dec 2024 | TRUE | 01 Mar 2025 | 900
INS-2025-009 | UP-2024-032 | 02 Jun 2025 | Safety | Island Inspection Services | Pass | 1 | FALSE |  |  |  | 850
INS-2025-034 | UP-2024-110 | 03 Dec 2025 | Safety | Ulu SafeCheck Pte Ltd | Fail | 6 | TRUE | 04 Feb 2025 | TRUE | 14 Apr 2025 | 850
INS-2025-051 | UP-2024-110 | 05 Aug 2025 | Structural | Island Inspection Services | Fail | 4 | TRUE | 29 May 2025 | TRUE | 06 Jun 2025 | 900
INS-2025-088 | UP-2024-110 | 15 Sep 2025 | Safety | Ulu SafeCheck Pte Ltd | Fail | 3 | TRUE | 10 Jun 2025 | TRUE | 14 Oct 2025 | 850
INS-2026-004 | UP-2024-110 | 20 Jan 2026 | Structural | Island Inspection Services | Pass | 1 | FALSE |  |  |  | 900
INS-2024-095 | UP-2024-035 | 06 Oct 2024 | Structural | Pulau Ulu Safety Assessors Pte Ltd | Pass | 1 | TRUE | 25 Jun 2024 | TRUE |  | 2800
INS-2024-201 | UP-2024-035 | 15 Oct 2024 | Safety | Pulau Ulu Safety Assessors Pte Ltd | Conditional Pass | 3 | TRUE | 30 Oct 2024 | TRUE | 11 May 2024 | 2800
INS-2025-030 | UP-2025-012 | 20 Mar 2025 | Safety | Meridian Inspection Services | Pass | 1 | FALSE |  |  |  | 3200
INS-2025-078 | UP-2025-012 | 06 Dec 2025 | Structural | Meridian Inspection Services | Conditional Pass | 4 | TRUE | 30 Jun 2025 | TRUE | 07 Aug 2025 | 3200
INS-2025-112 | UP-2025-012 | 18 Sep 2025 | Safety | Meridian Inspection Services | Fail | 7 | TRUE | 10 Oct 2025 | FALSE | 22 Oct 2025 | 3200
INS-2025-149 | UP-2025-012 | 22 Oct 2025 | Safety | Meridian Inspection Services | Fail | 6 | TRUE | 15 Nov 2025 | FALSE | 12 Oct 2025 | 3200
INS-2025-188 | UP-2025-012 | 12 Oct 2025 | Safety | Meridian Inspection Services | Fail | 8 | TRUE | 01 May 2026 | FALSE |  | 3200
INS-2025-061 | UP-2025-058 | 15 Jul 2025 | Safety | Pulau Ulu Safety Assessors Pte Ltd | Pass | 2 | TRUE | 30 Jul 2025 | TRUE |  | 2800
INS-2025-130 | UP-2025-058 | 20 Oct 2025 | Structural | Pulau Ulu Safety Assessors Pte Ltd | Conditional Pass | 5 | TRUE | 11 Oct 2025 | FALSE | 25 Nov 2025 | 2800
INS-2025-171 | UP-2025-058 | 25 Nov 2025 | Structural | Pulau Ulu Safety Assessors Pte Ltd | Fail | 6 | TRUE | 20 Dec 2025 | FALSE |  | 2800
INS-2026-015 | UP-2025-058 | 18 Feb 2026 | Safety | Pulau Ulu Safety Assessors Pte Ltd | Fail | 9 | TRUE | 15 Mar 2026 |  |  | 2800
INS-2026-042 | UP-2025-012 | 03 May 2026 | Safety | Meridian Inspection Services | [6 empty] | 3200